# Westbrook Avenue Field Change Orders and RFI Register

Project file: Westbrook Avenue reconstruction and drainage upgrade. Record date: 2026-06-02. Station control basis: SC-2026-REV-B.

# 1. RFI and field change order status register

| source_id | record | date | subject | status | controlling statement | affected files or assets |
| --- | --- | --- | --- | --- | --- | --- |
| RFI-001 | RFI-004 | 2026-05-12 | Inlet naming at Pine Street | closed | CB-15A is an alias for CB-15 and must not be added as a separate asset. | WBK_asset_inventory_and_station_control.csv; WBK_storm_network_inspection_log.csv |
| RFI-002 | RFI-006 | 2026-05-16 | CB-14 station and legacy CI-14 label | closed | The inlet at the Westbrook sag point is CB-14 at Station 0+735.4; CI-14-OLD is a legacy paint or GIS label. | WBK_asset_inventory_and_station_control.csv; WBK_topographic_survey_points.csv |
| RFI-003 | RFI-009 | 2026-05-19 | CB-14 to MH-17 pipe slope | open | Do not accept 0.45 percent profile slope until survey-derived slope and city minimum slope are reconciled. | WBK_hydrology_rainfall_runoff_calcs.xlsx; WBK_topographic_survey_points.csv |
| RFI-004 | FCO-003 | 2026-05-23 | Pavement treatment 0+610 to 0+760 | approved | Revise the rehabilitation classification to full-depth reconstruction with subgrade stabilization in the weak support zone. | WBK_pavement_cores_and_deflection_tests.csv; WBK_geotechnical_boring_summary.docx |
| RFI-005 | RFI-012 | 2026-05-24 | Gas-main clearance at Station 0+820 | open | Vertical clearance is unresolved until the gas main depth is confirmed by pothole or utility-owner exposure record. | WBK_utility_markout_and_conflict_log.csv |
| RFI-006 | FCO-005 | 2026-05-26 | Pine Street ADA ramps | approved | Replace NE and SW Pine Street ramps because survey grades exceed city ADA criteria. | WBK_topographic_survey_points.csv; WBK_city_design_criteria_excerpt.docx |
| RFI-007 | RFI-015 | 2026-05-27 | Use of public flood photos for design storm | closed | Complaint photos support location and timing of flooding but do not establish the design-storm recurrence interval. | WBK_public_complaints_and_flood_photos.pdf |
| RFI-008 | FCO-007 | 2026-05-29 | Temporary inlet cleaning at CB-14 | closed | Cleaning is a maintenance action and does not resolve pipe slope, inlet spread, or sag-point profile issues. | WBK_storm_network_inspection_log.csv |

# 2. Detailed RFI notes

RFI-002: The station control correction for CB-14 resolves the CB-14 versus CI-14-OLD identity conflict. The signed survey and RFI closeout supersede the legacy GIS station 0+730 value.

RFI-003: The hydrology workbook profile note lists a 0.45 percent slope for the 450 mm pipe between CB-14 and MH-17. The survey points place CB-14 invert out at 101.832 m and MH-17 incoming invert at 101.548 m, with a station-derived plan length of approximately 86.2 m. The resulting slope is lower than the profile note and must be carried as a conflict until the design profile is revised.

RFI-004: The pavement management network summary recommends mill-and-overlay for the 0+600 to 0+800 range, but the field change order approves full-depth reconstruction from 0+610 to 0+760 because station-specific FWD and CBR data show weak support.

RFI-005: The gas-main vertical clearance cannot be resolved using the preliminary profile assumption. NorthStar Gas did not provide a depth at 0+820, and the old 0+807 pothole cannot be transferred across the conflict location.

RFI-006: The NE Pine ramp cross-slope and SW Pine ramp running-slope issues are both compliance failures against city criteria. The compliance summary that previously listed pass status is superseded by the 2026 signed survey.

# 3. Superseded or rejected assumptions

| source_id | assumption | reason rejected | controlling record |
| --- | --- | --- | --- |
| RFI-R1 | CB-14 located at Station 0+730.0 | Legacy GIS station was shifted; signed survey and RFI-006 control the station. | SV-096 to SV-098; RFI-002 |
| RFI-R2 | CB-14 to MH-17 pipe slope is 0.45 percent | Preliminary hydrology profile conflicts with survey-derived invert and length data. | SV-097 and SV-101; RFI-003 |
| RFI-R3 | 0+610 to 0+760 can receive mill-and-overlay | Weak subgrade and FWD results trigger full-depth treatment. | FCO-003; GEO-L3; GEO-L4; PAV-031 to PAV-038 |
| RFI-R4 | Gas-main cover can be assumed from the profile sheet | Utility clearance requires confirmed depth at the conflict station. | UTIL-021; UTIL-024; RFI-005 |
| RFI-R5 | Public photos establish a 25-year design storm | Complaints establish location and timing only; design storm is controlled by city criteria. | RFI-007; CRIT-D1 |

# 4. Open items at record close

| source_id | open item | why unresolved | required record |
| --- | --- | --- | --- |
| RFI-O1 | CB-14 to MH-17 design profile | Survey-derived slope conflicts with preliminary profile slope. | Revised profile calculation or approved redesign record. |
| RFI-O2 | Gas-main vertical clearance at 0+820 | Depth at conflict station was not exposed or confirmed by utility owner. | Pothole log or utility-owner depth confirmation at Station 0+820. |
| RFI-O3 | Permanent sag-point inlet spread check | Hydrology workbook used preliminary 10-year assumptions for a sag location. | Criteria-compliant 25-year spread and ponding check. |
| RFI-O4 | Utility markout validity at construction date | Markout dates expire before scheduled utility exposure. | Renewed markout record prior to excavation. |